## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Student | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail /OTP
1 | SB1/US2 | Student | Receive A Confirmation Mail/OTP | I Can Access The Assesment portal
1 | SB1/US3 | Student | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile
1 | SB1/US4 | Student | View The Subject Detalis | I Can See The Marking Scheme
1 | SB1/US5 | Student | View The Topic details of particular subject | I Can give exam according to the subject
1 | SB1/US6 | Student | Modify The Account Password | I Can Keep My Account Secure
1 | SB1/US7 | Student | Give Feedback/Suggestions | The Way Of Working Of Application Can Be Improved
1 | SB1/US8 | Student | give the exam | register user can give the exam
1 | SB1/US9 | Student | select the subjet for the exam | user can select the subject for the exam
1 | SB1/US10 | Student | View My Result | I Can Analyze My Performance
1 | SB1/US11 | Student | Discuss Among Other Students | I Can Share My Experience
DATABASE
2 | SB2/US12 | DBA | create database | create database for application
2 | SB2/US13 | DBA | create tables | Create tables for the database
2 | SB2/US14 | DBA | create connectivity with database | connectivity with database
2 | SB2/US15 | DBA | fire the queries | fire the query
2 | SB2/US16 | DBA | Fire Insert Queries | I Can Insert New Records In The Database
2 | SB2/US17 | DBA | Fire Select Queries | I Can View The Records
2 | SB2/US18 | DBA | Fire Update Queries | I Can Keep The Database Updated
2 | SB2/US19 | DBA | Fire Delete Queries | I Can Remove Unwanted questions
2 | SB2/US20 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use
2 | SB2/US21 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More
ADMIN
3 | SB3/US22 | ADMIN | Login Into The System Using Mail Id And Password | I Can Access The Assesment Portal
3 | SB3/US23 | ADMIN | Modify The Account Password | I Can Keep My Account Secure
3 | SB3/US24 | ADMIN | Finalize The Subjects For Test | Test Allotment Subject Can Be Done
3 | SB3/US25 | ADMIN | Add The Questions | Add the Question Of all Subjects
3 | SB3/US26 | ADMIN | Allot The Subjects to be Test | Decide the subject to Test
3 | SB3/US27 | ADMIN | Add some notes about the topic | some idea about about the topic
3 | SB3/US28 | ADMIN | View The Result List Of The Students | I Can Monitor The Performance Of The Students
3 | SB3/US29 | ADMIN | Handle complete data of user | I handle complete data of user
4 | SB4/US30 | ADMIN | handle the complete database | I handle the complete database
4 | SB4/US31 | ADMIN | Upload Excel Sheet of questions | I can upload excel sheet of question
4 | SB4/US32 | ADMIN | edit the marks of question | I can edit the marks of the question
4 | SB4/US33 | ADMIN | provide a negative marking | I can provide negative marking
4 | SB4/US34 | ADMIN | manage result | I can manage the result
4 | SB4/US35 | ADMIN | manage questions | I can manage the question
4 | SB4/US36 | ADMIN | manage the answers of the question | I can manage the answer of the question
4 | SB4/US37 | ADMIN | provide the facility to choose the sector of exam | I can provide the facility to choose the sector of the exam
4 | SB4/US38 | ADMIN | handle the user request for forget password | I can handle the user forget password
4 | SB4/US39 | ADMIN | update the password in database | I can update the password in database
4 | SB4/US40 | ADMIN | Add the questions | I can add the questions
4 | SB4/US41 | ADMIN | add new subject for test | I can add new subject for test
4 | SB4/US42 | ADMIN | add answer of the questions | I can add answer of the question

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Assessment Portal>
SB1/US1 | Registration | SB1/D1/T1 | firstly we make signup page using android in xml file | PS | COMPLETED | 23-09-2018
|  | SB1/D1/T2 | use validation in sign up page | SJ | COMPLETED | 23-09-2018
|  | SB1/D1/T3 | write code for sign up page in java | PS+SJ | COMPLETED | 23-09-2018
|  | SB1/D1/T4 | create connectivity with database using php | PS+RK | COMPLETED | 23-09-2018
|  | SB1/D1/T5 | create database for store the data | RK | COMPLETED | 23-09-2018
|  | SB1/D1/T6 | fire the insert query for store data | SJ+RK | COMPLETED | 23-09-2018
SB1/US2 | Registration verification | SB1/D2/T1 | there is pop-up for success completion | SJ | COMPLETED | 23-09-2018
|  | SB1/D2/T2 | Email for verification write code in java file | PS+SJ | COMPLETED | 23-09-2018
|  | SB1/D2/T3 |  |  | COMPLETED
|  | SB1/D2/T4 |  |  | COMPLETED
|  | SB1/D2/T5 |  |  | COMPLETED
SB1/US3 | Login | SB1/D3/T1 | we make login page using android inXml file | PS | COMPLETED | 26-09-2018
|  | SB1/D3/T2 | use validation in Login page | SJ | COMPLETED | 26-09-2018
|  | SB1/D3/T3 | fire the insert query for store data | PS+SJ | COMPLETED | 26-09-2018
|  | SB1/D3/T4 | fire the select query for store data | PS+RK | COMPLETED | 26-09-2018
SB1/US6 | Forget Password | SB1/D4/T1 | using android we code for forget password | RK | COMPLETED
|  | SB1/D4/T2 |  |  | COMPLETED
|  | SB1/D4/T3 |  |  | COMPLETED
|  | SB1/D4/T4 |  |  | COMPLETED
|  | SB1/D4/T5 |  |  | COMPLETED | 26-09-2018
SB1/US7 | Modify account | SB1/D5/T1 | we create some edit link to edit an account | SJ | COMPLETED | 26-09-2018
|  | SB1/D5/T2 | we make forget password to modify account | PS+SJ | COMPLETED
SB1/D5/T3
SB1/D5/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PS | Pankaj Sharma
| RK | Ravi Kumawat
| SJ | Sunil Jangid
Verified By:
MR. Praveen Gupta

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 15 | 15 | Tasks
2018-09-12 | 11 | 12
2018-09-11 | 7 | 8
2018-09-14 | 4 | 6
2018-09-16 | 2 | 3
2018-09-18 | 0 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Assessment Portal>
SB2/US1 | Add user | SB2/D1/T1 | Designing the GUI | PS | COMPLETED | 2018-10-10
|  | SB2/D1/T2 | Connection with database to fetch the data | RK | COMPLETED | 2018-10-10
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RK+PS+SJ | COMPLETED | 2018-10-10
SB2/US2 | Register student | SB2/D2/T1 | Designing of GUI | SJ | COMPLETED | 2018-10-10
|  | SB2/D2/T2 | Validating user input at client level | RK | COMPLETED | 2018-10-10
|  | SB2/D2/T3 | Validating user input at server level | SJ | COMPLETED | 2018-10-10
|  | SB2/D2/T4 | Connection with Database to insert the record. | PS | COMPLETED | 2018-10-10
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RK+PS+SJ | COMPLETED | 2018-10-10
SB2/US3 | Exam | SB1/D6/T1 | selection of exam provided to select | RK | COMPLETED | 2018-10-10
|  | SB1/D6/T2 | we make layout to select subject | RK | COMPLETED | 2018-10-10
|  | SB1/D6/T3 |  |  | COMPLETED
|  | SB1/D6/T4 |  |  | COMPLETED
|  | SB1/D6/T5 |  |  | COMPLETED
SB2/US4 | Question | SB1/D7/T2 | here we use check box to select the option | SJ | COMPLETED | 26/10/2018
|  | SB1/D7/T3 | here is skip and next or submit button | SJ | COMPLETED | 26/10/2018
|  | SB1/D7/T4 |  |  | COMPLETED
|  | SB1/D7/T5 |  |  | COMPLETED
SB2/US5 | Result | SB1/D8/T1 | after exam user fatch the the result from the database | PS+RK | COMPLETED | 26/10/2018
|  | SB1/D8/T2 | user use select query | PS+SJ | COMPLETED | 26/10/2018
|  | SB1/D8/T3 | first store using insert query | PS | COMPLETED | 26/10/2018
|  | SB1/D8/T4 |  |  | COMPLETED

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PS | Pankaj Sharma
| RK | Ravi Kumawat
| SJ | Sunil Jangid
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 15 | 15 | Tasks
2017-09-28 | 13 | 14
2017-10-02 | 11 | 12
2017-10-05 | 7 | 9
2017-10-07 | 3 | 5
2017-10-09 | 0 | 0
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Assessment Portal>
SB3/US1 | Login | SB1/D3/T1 | we make login page using android inXml file | PS | COMPLETED | 26-10-2018
|  | SB1/D3/T2 | use validation in Login page | PS+RK | COMPLETED | 26-10-2018
|  | SB1/D3/T3 | fire the insert query for store data | SJ+RK | COMPLETED | 26-10-2018
|  | SB1/D3/T4 | fire the select query for store data | SJ | COMPLETED | 26-10-2018
SB3/US2 | Forget password | SB1/D4/T1 | using android we code for forget password | PS+SJ | COMPLETED | 26-10-2018
SB1/D4/T2
SB1/D4/T3
SB1/D4/T4
SB3/US3 | Modify Account | SB1/D5/T1 | we create some edit link to edit an account | RK | COMPLETED | 26-10-2018
|  | SB1/D5/T2 | we make forget password to modify account | RK+SJ | COMPLETED | 26-10-2018
SB1/D5/T3
SB1/D5/T4
SB3/US4 | Exams | SB1/D6/T1 | create page for exams using layout | PS | COMPLETED | 26-10-2018
|  | SB1/D6/T2 | for every exam provide different button to click on that | PS+SJ | COMPLETED | 26-10-2018
SB1/D6/T3
SB1/D6/T4
SB3/US5 | Questions | SB1/D7/T2 | here we use check box to select the option | PS | COMPLETED | 26-10-2018
|  | SB1/D7/T3 | here is skip and next or submit button | PS+RK | COMPLETED | 26-10-2018
|  | SB1/D7/T4 | can upload excel for the questions | SJ+RK | COMPLETED | 26-10-2018
SB1/D7/T5
SB3/US6 | Result | SB1/D8/T1 | after exam user fatch the the result from the database | PS+RK+SJ | COMPLETED | 26-10-2018
|  | SB1/D8/T2 | user use select query | PS+RK | COMPLETED | 26-10-2018
|  | SB1/D8/T3 | first store using insert query | SJ+RK | COMPLETED | 26-10-2018
SB1/D8/T4
SB3/US7 | Add Subject | SB2/D6/T1 | Designing of GUI | PS | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T2 | Validating user input at client level | PS+RK | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T3 | Validating user input at server level | SJ+RK | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T4 | Connection with Database to insert the record. | SJ | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | PS+RK+SJ | NOT COMPLETED | 2018-03-11
SB3/US8 | Add Question | SB2/D6/T1 | Designing of GUI | PS | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T2 | Validating user input at client level | PS+RK | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T3 | Validating user input at server level | SJ+RK | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T4 | Connection with Database to insert the record. | SJ | NOT COMPLETED | 2018-03-11
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | PS+RK+SJ | NOT COMPLETED | 2018-03-11

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 25 | 25 | Tasks
2018-10-18 | 21 | 25
2018-10-20 | 17 | 25
2018-10-21 | 10 | 25
2018-10-22 | 5 | 25
2018-10-23 | 0 | 25
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 -<Assessment Portal>
SB4/US1 | ADMIN | SB4/D1/T1 | Testing of recommendation system related to admin | PS | NOT COMPLETED | 15-01-2019
|  | SB4/D1/T2 | Testing of whole system application | RK | NOT COMPLETED | 15-01-2019
|  | SB4/D1/T3 | Testing of database related to admin | RK+PS+SJ | NOT COMPLETED | 15-01-2019
SB4/US2 | USER | SB4/D1/T1 | Testing of recommendation system related to user | SJ | NOT COMPLETED | 15-01-2019
|  | SB4/D1/T2 | Testing of whole system application | RK | NOT COMPLETED | 15-01-2019
|  | SB4/D1/T3 | Testing of database related to user | SJ | NOT COMPLETED | 15-01-2019
NOT COMPLETED
[5 empty] | NOT COMPLETED | 20-01-2019
SB4/US3 | DATABASE | SB4/D1/T1 | check the complete database | RK | NOT COMPLETED | 20-01-2019
|  | SB4/D1/T2 | check the query those are used | RK | NOT COMPLETED | 20-01-2019
|  | SB4/D1/T3 | check the table those are in the database | RK+PS+SJ | NOT COMPLETED | 20-01-2019

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 10 | 10 | Tasks
2019-01-11 | 7 | 10
2019-01-12 | 5 | 10
2019-01-13 | 3 | 10
2019-01-14 | 1 | 10
2019-01-15 | 0 | 10
0
Days